## GSA ADS Sprint 1
GSA ADS Development - SPRINT 1 - (22/Jun/15 10:00 AM - 24/Jun/15 1:51 PM)
Praeses JIRA
Displaying 5 issues at 06-30-15 11:19 AM.
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Reporter | Created | Updated | Resolved | Fix Version/s | Linked Issues | Environment | Description | Labels | Epic Link | Sprint | Epic/Theme | Story Points | Branch | Impediment | Flagged
GSA-ADS | ADS-2 | Setup GIT Repository | Technical Debt | Done | Medium | Fixed | James Baker | 2015-06-22 10:50 | 2015-06-22 16:20 | 2015-06-22 13:32 |  |  |  | Establish a public GIT Repository on one of the major providers such as GitHub, BitBucket, etc. |  | Project Setup | Sprint 1 |  | 1
GSA-ADS | ADS-3 | Setup codebase | Technical Debt | Done | Medium | Fixed | James Baker | 2015-06-22 11:07 | 2015-06-22 16:31 | 2015-06-22 14:13 |  |  |  | Setup base project elements and related Unit Test placeholders. |  | Project Setup | Sprint 1 |  | 2
GSA-ADS | ADS-4 | Setup hosted site | Technical Debt | Done | Medium | Fixed | James Baker | 2015-06-22 11:10 | 2015-06-24 10:57 | 2015-06-24 10:38 |  |  |  | Setup the hosted environment that will hold the deployed application. |  | Project Setup | Sprint 1 |  | 2
GSA-ADS | ADS-5 | Setup continuous integration | Technical Debt | Done | Medium | Fixed | James Baker | 2015-06-22 11:11 | 2015-06-24 10:57 | 2015-06-24 10:38 |  |  |  | Setup/configure the continuous integration that will build and test the code upon it being committed to the remote repository. |  | Project Setup | Sprint 1 |  | 2
GSA-ADS | ADS-8 | Technical Spike on Open FDA API and D3 visualization library | Technical Debt | Done | Medium | Done | James Baker | 2015-06-23 10:31 | 2015-06-23 13:57 | 2015-06-23 10:34 |  |  |  | Access the Open FDA API data and graph using the D3 visualization library to ensure this combination will work for the Prototype. |  |  | Sprint 1 |  | 4
Generated at Tue Jun 30 11:19:47 CDT 2015 by Brian Burgess using JIRA 6.1.5#6160-sha1:a61a0fc278117a0da0ec9b89167b8f29b6afdab2.

## GSA ADS Sprint 2
GSA ADS Development - SPRINT 2 - (25/Jun/15 10:00 AM - 29/Jun/15 1:11 PM)
Praeses JIRA
Displaying 10 issues at 06-30-15 11:28 AM.
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Reporter | Created | Updated | Resolved | Fix Version/s | Linked Issues | Environment | Description | Labels | Epic Link | Sprint | Epic/Theme | Story Points | Branch | Impediment | Flagged
GSA-ADS | ADS-9 | Work with Product Owner on identifying and designing Data Visualizations | Story | Done | Medium | Done | James Baker | 2015-06-23 10:33 | 2015-06-29 13:11 | 2015-06-29 13:07 | Sprint 2 |  |  | Using the Open FDA data schema, work with Product Owner on 2 or more Data Visualizations that will meet the needs for the prototype. |  |  | Sprint 2 |  | 4
GSA-ADS | ADS-10 | A researcher can see a visualization of adverse events for a suspect drug | Story | Done | Medium | Done | James Baker | 2015-06-23 10:36 | 2015-06-29 13:11 | 2015-06-29 10:31 | Sprint 2 | ADS-12 |  | The researcher should be able to display adverse event data for Suspect drugs (only) via a bubble chart. |  |  | Sprint 2 |  | 6 | 3-Develop
GSA-ADS | ADS-14 | Create mockup for drug event visualization | Story | Done | Medium | Done | Brian Burgess | 2015-06-23 12:58 | 2015-06-29 13:11 | 2015-06-29 13:07 | Sprint 2 | [5 empty] | Sprint 2 |  | 1
GSA-ADS | ADS-15 | Drug caching | Story | Done | Medium | Fixed | Brian Burgess | 2015-06-25 10:14 | 2015-06-29 13:11 | 2015-06-25 14:45 | Sprint 2 |  |  | The back-end should have an API for caching and pulling drug counts by date |  |  | Sprint 2 |  | 2
GSA-ADS | ADS-16 | Drug caching - location | Story | Done | Medium | Fixed | Brian Burgess | 2015-06-25 10:16 | 2015-06-29 13:11 | 2015-06-25 15:59 | Sprint 2 |  |  | Cache drug location by date |  |  | Sprint 2 |  | 2
GSA-ADS | ADS-17 | Graph drug events | Story | Done | Medium | Done | Brian Burgess | 2015-06-25 10:16 | 2015-06-29 13:11 | 2015-06-29 13:08 | Sprint 2 |  |  | Build graph to show drug event counts by date |  |  | Sprint 2 |  | 2
GSA-ADS | ADS-18 | Drug name caching | Story | Done | Medium | Fixed | Glen Wallace | 2015-06-25 15:58 | 2015-06-29 13:11 | 2015-06-26 11:08 | Sprint 2 |  |  | Cache the list of all possible drug names |  |  | Sprint 2 |  | 2
GSA-ADS | ADS-19 | Location name caching | Story | Done | Medium | Fixed | Glen Wallace | 2015-06-25 16:11 | 2015-06-29 13:11 | 2015-06-26 11:48 | Sprint 2 |  |  | Cache the list of all possible location names. |  |  | Sprint 2 |  | 2
GSA-ADS | ADS-20 | Clean up importers | Story | Done | Low | Done | Glen Wallace | 2015-06-26 13:10 | 2015-06-29 13:11 | 2015-06-29 13:08 | Sprint 2 |  |  | Importers currently have redundant code that should be consolidated and reused. |  |  | Sprint 2 |  | 1
Generated at Tue Jun 30 11:28:31 CDT 2015 by Brian Burgess using JIRA 6.1.5#6160-sha1:a61a0fc278117a0da0ec9b89167b8f29b6afdab2.

## GSA ADS Sprint 3
GSA ADS Development - SPRINT 3 - (29/Jun/15 10:00 AM - 7/Jul/15 10:00 AM)
Praeses JIRA
Displaying 4 issues at 07-07-15 8:53 AM.
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Reporter | Created | Updated | Resolved | Fix Version/s | Linked Issues | Environment | Description | Labels | Epic Link | Sprint | Epic/Theme | Story Points | Branch | Impediment | Flagged
GSA-ADS | ADS-12 | A researcher can filter suspect drug adverse events by geography and age | Story | Done | Medium | Fixed | James Baker | 2015-06-23 10:38 | 2015-07-07 08:44 | 2015-07-07 08:44 |  | ADS-10 |  | The bubble chart should be filterable by geography (country), gender (M/F) and age (0-12) with circle size indicating number of adverse reports for the drug and color coding showing the severity of the adverse event (Red=most serious). |  |  | Sprint 3 |  | 2
GSA-ADS | ADS-22 | Cache filterable imports by URL | Bug | Done | Medium | Fixed | Glen Wallace | 2015-06-29 13:34 | 2015-07-07 08:44 | 2015-07-07 08:44 |  |  |  | Adding the ability to filter caused the way we need to cache imports to change. They should now be cached by their URL in filterable imports. |  |  | Sprint 3 |  | 2
GSA-ADS | ADS-23 | Break url generation into its own method | Bug | Done | Medium | Fixed | Glen Wallace | 2015-06-29 13:38 | 2015-06-30 08:39 | 2015-06-29 15:20 |  |  |  | Currently the url generation is performed straight in the pull method. This generation should be broken out into its own method to make the code more readable. |  |  | Sprint 3 |  | 2
GSA-ADS | ADS-24 | Change class and filenames to match their new functionality | Bug | Done | Medium | Fixed | Glen Wallace | 2015-06-29 15:22 | 2015-06-30 08:39 | 2015-06-29 17:06 |  |  |  | Currently the names of the Importers and their containing files do not match their actual functionality due to functionality changes. _CountImporter should instead be called _CountByDateImporter _NameImporter should instead be called _CountImporter |  |  | Sprint 3 |  | 2
Generated at Tue Jun 30 11:33:17 CDT 2015 by Brian Burgess using JIRA 6.1.5#6160-sha1:a61a0fc278117a0da0ec9b89167b8f29b6afdab2.